## Sheet1
Prepared By: Mayur Sharma
DATE:05/04/2013
Bunga Indo SCHEDULE SHEET
Meetings | DATE | Resource | Task/Details | Requirement Id from SRS | Estimated Hours | Status (YES/NO) | Actual Hours | Time Difference
|  | Designer | PSD to HTML |  | 48
Admin End
| 2013-05-28 | Gaurav | Set Project on local. and start Template integration. |  | 8
|  | Sheetal | Rnd and read documents |  | 0
| 2013-05-29 | Gaurav | Template Completion. Deal of the day management at backend and home page linking. Static pages creation and linking. Contacts us page, newsletter signup. |  | 8
|  | Sheetal | User Registration- Add captcha and complete testing. Menu SubMenus linking |  | 8
| 2013-05-30 | Gaurav | Product Listing. Option of adding a highlight product in each category at backednd. Fronend management of hightlighed product on first page of category product listing. |  | 8
|  | Sheetal | Add tags feature for product at backend. Date range option and region option for product. |  | 8
| 2013-05-31 | Gaurav | RND for payment gateway(Doku). |  | 8
|  | Sheetal | Login,Logout/edit profile of registered user as per layout. Add option at backend for taking time to expire a order request. |  | 8
| 2013-06-03 | Gaurav | Paymnet Gateway integration and checkout process testing. |  | 8
|  | Sheetal | upsell product selling. Point system concept integration while checkout |  | 8
| 406306 | Gaurav | Vendor/admin notification after order placed. Only to those vendor which in that order region. Address book management of user. |  | 8
|  | Sheetal | Shopping cart management according to design and flow. |  | 8
Milestone 1 5-June-2013 | 2013-06-05 | Gaurav | Vendor module. Register/Login vendor at backend. Listing,Edit, Delete |  | 8
|  | Sheetal | advertise management at backend. Show one banner at product listing page top and one at sidebar. |  | 8
| 2013-06-06 | Gaurav | Listing,Edit, Delete of vendor at backend. |  | 8
|  | Sheetal | advertise management at backend. Show one banner at product listing page top and one at sidebar. |  | 8
| 2013-06-07 | Gaurav | Testing complete flow and bug fixing |  | 8
|  | Sheetal | Testing complete flow and bug fixing |  | 8
| 2013-06-10 | Gaurav | Advance search on home page. |  | 8
|  | Sheetal | Front end vendor Management. Accept order and manage Status. |  | 8
| 2013-06-11 | Gaurav | Advance search on home page. |  | 8
|  | Sheetal | Live chat integration |  | 8
| 2013-06-12 | Gaurav | Integrate Auto watermark images for product. Integration Testing |  | 8
|  | Sheetal | Tag of discount on images as badges for products. Integration Testing. |  | 8
| 2013-06-13 | Gaurav | Order Management at backend- Admin can assign to vendor. If not accepted by vendor then flag setting for refund or points giving. |  | 8
|  | Sheetal | Cron for email sending if in a given time period order is not accepted by any vendor. |  | 8
Milestone 2 14-June-2013 | 2013-06-14 | Gaurav | Fronend login to vendor Orders listing to vendor. |  | 8
|  | Sheetal | Forgot/Change Password and edit profile for vendor at frontend. |  | 8
| 2013-06-17 | Gaurav | Option to print invoice at admin with 2 options. 1) Invoice 2)Delivery Note New screen for delivery note to select products option. |  | 8
|  | Sheetal | Rnd on pdf integration for invoices at admin side. |  | 8
| 2013-06-18 | Gaurav | Populate all static pages content. Footers icon linking. |  | 8
|  | Sheetal | Invoice/Delivery note pdf generation. |  | 8
Beta Release | 2013-06-19 | Gaurav | Full Integration Testing |  | 8
|  | Sheetal | Full Integration Testing |  | 8
| Total |  |  |  | 264

## Sheet2
Admin End
2013-05-06
2013-05-07 |  | Admin Login. Forgot password ,Left section for manage admin section with their links
2013-05-08 |  | Manage Stats | 3 | 6
2013-05-09
2013-05-10
406284
406285
2013-05-15
2013-05-16 |  |  |  | 12
2013-05-17
2013-05-20 |  | Check Invoices |  | 4
Supervisor End
2013-05-21 | Sameer K | Login |  | 2
2013-05-21 | Sameer K | Forgot Password |  | 2
2013-05-22 | Sameer K | Manage Members |  | 8
2013-05-22 | Sameer K | Select & Export Members |  | 8
2013-05-23 | Sameer K | Email Template Setup |  | 4
Front End
2013-05-24 |  |  |  | 8
2013-05-27 | Sameer K
2013-05-27 | Sameer K | Home Page | 14 | 6
2013-05-28 | Sameer K | Registration | 15 | 8
2013-05-29 | Sameer K | Registration | 15 | 16
2013-05-30 | Sameer K | Manage Rating | 16 | 8
2013-05-31 | Sameer K | Chat | 17 | 8
2013-06-03 | Sameer K | Chat | 17 | 8
2013-06-04 | Sameer K | Chat | 17 | 8
2013-06-05 | Sameer K | Chat | 17 | 8
2013-06-06 |  | Professional Categories Display search results with respective category selected in dropdown | 18 | 8
2013-06-07 | Sameer K | Professional Categories Display search results with respective category selected in dropdown | 18 | 8
2013-06-10 | Sameer K | Casting Call Add / View / Search |  | 8
2013-06-11 | Sameer K | Casting Call Add / View / Search | 19 | 8
2013-06-12 |  | Message 1) Inbox 2) Send 3) My Folder | 21 | 8
2013-06-13 |  | Message 1) Inbox 2) Send 3) My Folder | 21 | 8
2013-06-14 |  | Manage Admin Area Display All Links to various section of member Implement Below sections for members 1) Edit Profile 2) Locations 3) Advice(link to blog page for paid members only) 4) My Alerts(Notification) 5) Invoices 6) Social Media Network | 22 | 32
2013-06-20
2013-06-21
2013-06-24 |  | Calendar
2013-06-25
2013-06-26
2013-06-27
2013-06-28
2013-07-01
2013-07-02
2013-07-03
2013-07-04
2013-07-05
2013-07-07
2013-07-07
2013-07-08
2013-07-08
2013-07-09 | Sameer K | Testing+ Bug Fixing | N/A | 32
2013-07-15 | Client | Beta release
|  | Bug fixing |  | 16
| Mayur/Sameer K | Set site on live |  | 8
Total |  |  |  | 476